## CPIE Schedule
CPIE — Climate Policy Intelligence Engine
AI Engineering Buildcamp Capstone · Project Schedule & Tracker
🔴 Course Deadline |  | Status options → | ⬜ Not Started | 🔄 In Progress | ✅ Done | ⚠️ At Risk
🟡 Self-checkpoint
# | Week | Date | Type | Task / Deliverable | Course Deadline | Status | Notes
1 | Week 2 | Wed 13 May | 🟡 Checkpoint | Start PoC — ingestion + retrieval pipeline begun 3 PDFs chunked, embedded, FAISS indexed, BM25 initialised | — | ⬜ Not Started | Adapt retrieval modules from QueryLens
2 | Week 2 | Tue 19 May | 🔴 Deadline | Project Card due One paragraph: problem · user · input · processing · output · success metric | ✅ Required | ⬜ Not Started | Draft in CPIE Project on Claude
3 | Week 3 | Fri 29 May | 🟡 Checkpoint | End-to-end pipeline working via CLI One query → hybrid retrieval → Haiku synthesis → structured JSON brief | — | ⬜ Not Started | No UI needed yet. Get one query working cleanly.
4 | Week 3 | Fri 29 May | 🔴 Deadline | Simple E2E version of the project Full pipeline: ingest → retrieve → rerank → synthesise → output | ✅ Required | ⬜ Not Started | Aligns with checkpoint above — same deliverable
5 | Week 4 | Wed 4 Jun | 🟡 Checkpoint | Write ground truth QA dataset (25–35 pairs) DO THIS BEFORE running eval — write questions from reading, not from retrieval outputs | — | ⬜ Not Started | Include 5–8 negatives (out-of-corpus queries)
6 | Week 5 | Fri 13 Jun | 🔴 Deadline | Tests + Monitoring + Evaluation in place Unit tests · LLM-as-judge · query logging · Streamlit monitoring dashboard | ✅ Required | ⬜ Not Started | All three must be present — don't leave monitoring for week 6
7 | Week 6 | Mon 16 Jun | 🟡 Checkpoint | Docker + Makefile + README polish Reproducibility pass: clean setup instructions, accessible data, architecture diagram | — | ⬜ Not Started | README is a deliverable, not an afterthought
8 | Week 6 | Fri 20 Jun | 🔴 Deadline | Deployed demo + clean README + walkthrough Live demo accessible, README complete, short walkthrough video or doc | ✅ Required | ⬜ Not Started | Final submission — buffer time is Mon–Thu 16–19 Jun

## Rubric Tracker
CPIE — Rubric Tracker
Category | Max | Projected | Actual | Notes
Problem description (README) | 2 | 2 |  | Clear problem, clear user — write this first
RAG / knowledge base | 2 | 2 |  | Core of the project
Agents / LLM (RAG workflow) | 3 | 2 |  | RAG workflow = 2; no agent layer in v1
Code organisation | 2 | 2 |  | Proper modules, not notebooks
Testing (unit + judge tests) | 2 | 2 |  | Both achievable — build during week 3–4
Evaluation (ground truth dataset) | 3 | 3 |  | Swing factor: quality of QA pairs
Monitoring (logs + dashboard) | 2 | 2 |  | Logs + Streamlit dashboard
Reproducibility | 2 | 2 |  | Clear README, public PDFs as data source
Best practices bonus (Docker, Makefile) | 7 | 4 |  | Docker + Makefile realistic; CI/CD is stretch
UI / deployment bonus | 3 | 2 |  | Streamlit UI is achievable
TOTAL | 28 | 23 | 0 | Pass threshold: 12 pts ¦ Target: 22–27 pts